## Sheet1
Transaction | Header Status - Item Status | Updated Status | Qty. Reference | Estimate (day) | NOTE | status (create query) | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17
A. In transit
1. Store Transfer | In Transit - In Transit | Received - Transferred | Iss. Qty | 2 | less than 10 records, should do it manually | Done
B. Dues in
1. Store Requisition | Submitted - Reserved | Cancelled | Req. Qty | 2 |  | Done | 2019-09-26: 0.25; 2019-09-27: 1
2. Store Transfer | Submitted Request - Reserved | Cancelled | Req. Qty | 0.25 | Same with dues-out | Done | 2019-09-30: 0.5
| Submitted Request - Approved Request | Cancelled | Req. Qty | 0.25 |  | Done
| Submitted - Reserved | Cancelled | Req. Qty | 0.25 |  | Done
| Submitted - Approved | Cancelled | Req. Qty | 0.25 |  | Done
| Approved Request - Approved Request | Cancelled | Req. Qty | 0.25 |  | Done
| Approved - Cancelled | Cancelled | Req. Qty | 0.25 |  | Done
| Approved - Approved | Cancelled | Req. Qty | 0.25 |  | Done
| Approved - Completed | Cancelled | Req. Qty | 0.25 |  | Done
3. Purchase Order | Printed - Approved | Cancelled | Qty Req | 2 |  | Done | 2019-09-30: 0.5; 2019-10-01: 1
C. Dues Out
1. Prescription (compound and non compound) | Submitted - Reserved | Cancelled | Req. Qty | 2 | NOT COMPOND AND NOT ADDED TO INVOICVE | Done
| Submitted - Completed | Cancelled | Req. Qty | 1 |  | Done
| Partially Dispensed - Issued | Issued | Rcvd. Qty | 1 |  | Done
| Allocated - Completed | Unclaim | Alloc. Qty | 1 |  | Done
2. Store Requisition | Submitted - Cancelled | Cancelled | Req. Qty | 2 |  | Done
| Submitted - Issued | Cancelled | Req. Qty | 1 |  | Done
| Submitted - Reserved | Cancelled | Req. Qty | 1 |  | Done
3. Store Transfer | Submitted Request - Reserved | Cancelled | Req. Qty | 2.25 | Do first | Done | 2019-09-23: 1; 2019-09-24: 0.5; 2019-09-25: 0.5
| Submitted Request - Approved Request | Cancelled | Req. Qty | 0.25 |  | Done | 2019-09-25: 0.5
| Submitted - Reserved | Cancelled | Req. Qty | 0.25 |  | Done
| Submitted - Approved | Cancelled | Req. Qty | 0.25 |  | Done
| Approved Request - Approved Request | Cancelled | Req. Qty | 0.25 |  | Done | 2019-09-26: 0.75
| Approved - Cancelled | Cancelled | Req. Qty | 0.25 |  | Done
| Approved - Approved | Cancelled | Req. Qty | 0.25 |  | Done
| Approved - Completed | Cancelled | Req. Qty | 0.25 |  | Done
D. Outstanding In
1. Store Transfer (outstanding flag) | Approved - Approved | Cancelled | Req. Qty | 0.25 |  | Done | bar: 2019-10-03 to 2019-10-04
| Approved - Cancelled | Cancelled | Req. Qty | 0.25
| Approved - Completed | Cancelled | Req. Qty | 0.25
| Approved - Transferred | Cancelled | Req. Qty | 0.25 | should do it manually
| Approved Request - Approved Request | Cancelled | Req. Qty | 0.25
| Received - Transferred | Cancelled | Req. Qty | 0.25
| Submitted - Reserved | Cancelled | Req. Qty | 0.25
| Submitted - Approved | Cancelled | Req. Qty | 0.25
| Submitted Request - Reserved | Cancelled | Req. Qty | 0.25
| Submitted Request - Approved Request | Cancelled | Req. Qty | 0.25
E. Outstanding Out
1. Store Transfer (outstanding flag) | Approved - Approved | Cancelled | Req. Qty | 0.25 |  | Done | 2019-10-07: 0.75
| Approved - Cancelled | Cancelled | Req. Qty | 0.25
| Approved - Completed | Cancelled | Req. Qty | 0.25
| Approved - Transferred | Cancelled | Req. Qty | 0.25 | should do it manually
| Approved Request - Approved Request | Cancelled | Req. Qty | 0.25
| Received - Transferred | Cancelled | Req. Qty | 0.25
| Submitted - Reserved | Cancelled | Req. Qty | 0.25
| Submitted - Approved | Cancelled | Req. Qty | 0.25
| Submitted Request - Reserved | Cancelled | Req. Qty | 0.25
| Submitted Request - Approved Request | Cancelled | Req. Qty | 0.25
2. Prescription (outstanding) | Allocated - Issued | Issued | Rcvd. Qty | 1 | less than 10 records, should do it manually | Done | 2019-10-07: 0.25; 2019-10-08: 0.5
| Edited - Reserved | Cancelled | Req. Qty | 1 |  | in-progress
| Issued - Issued | No Outstanding |  | 1 | Should do 2.1 first | Done | 2019-10-08: 0.5
| Partially Dispensed - Issued | Unclaim | Alloc. Qty | 1 | there is no record, maybe they are updated in dues-out | Done
3. Medication Chart (outstanding) | Administered - Administered | Stopped | Qty. Rcvd. | 2 | less than 10 records, should do it manually | Done
F. RO
1. Purchase Order | Approved - Approved | Cancelled - New | Qty Req | 2 |  | Done | bar: 2019-10-02
| Approved - PO Created | Cancelled - New | Qty Req | 1 | I will do this case after update data for dues-in PO | wait for update dues-in PO
|  |  | Total: | 35 | day (s)